# Marketing plan – a template

A marketing plan is a tool that helps – and forces you to think in a structured way how you will market and sell your products and services. When you write down your plans they tend to be more real and fit for use.

You find:

1. Action plan for sales- and marketing activities

In this template you must write how you will manage the marketing in your business month by month. You might have an underlying description of the activities on another sheet of paper.  When all the months are filled in you will have a good view of how you promote your business.

2. Calendar that shows what and when the activities will take place

This template focuses on what you want to do and when you will do it. It always helps to put dates on the activities if you want to get it done. When filled out you can overview if you have the resources to execute your plans. If your marketing plan is not too complex you might do with the action plan and leave out the calendar.

Example:

Action plan for sales- and marketing activities, 2015

– Example from a wholesale business in decorative art and kitchen utensils

| Month | Activity we will implement | Deadline | Responsible |
| --- | --- | --- | --- |
| January | - Before the end of January a meeting with one of the larges retailer of decorative art and kitchen utensils chains must be set up in order to establish a Shop-in-Shop concept. - Update web site (every month) | 31/1 | Amish Charu |
| February | - Participate in the national decorative art and kitchen utensils trade fair. Sales pitch ordered and manned. - At the sales pitch: “Give us your business card and participate in competition – and receive Newsletter” - Establish two home parties where our kitchen utensils and Vijay’s food meets - All contacts from the trade fair must be contacted and meetings must be set up. Goal: 50 % will buy from us - Update web site | 2/2 15/2 27/2 | Amish Charu Charu Amish Charu |
| March | - Newsletter module must be bought for our web site and existing customers uploaded to newsletter database – if we get their permission. - Update web site | 30/3 30/3 | Charu Charu |
| April | - PR articles are sent to provincial news papers and magazines about our new gourmet kitchen knife series - Follow up on PR articles – call the news papers and magazines - Update web site | 20/4 30/4 | Charu Amish Charu |
| May | - Go through costumer database and find costumers what have bought for under 750 $. Contact them for more sales or remove them from database. Goal: Do not waste time on “time robbers” - Arrange photo shooting for new catalogue - Update web site | 30/5 20/5 | Charu Amish Charu |
| June | - Concept for ”New Year gifts” is investigated – focus on local businesses - New Year and Christmas sales are prepared. - Newsletter about New year and Christmas sales is sent to costumers - Update web site | 25/6 30/6 | Amish Amish Charu Charu |
| July | - Update web site |  | Charu |
| August | - PR articles are send to national magazines about our new gourmet kitchen knife series - Follow up on PR articles – call the magazines - Update web site | 20/8 30/8 | Charu Charu Charu |
| September | - Analyze the effect of the Newsletter. Can we do better and create extra sales? - Analyze web site. How many visitors? What do the read? Do they purchase products or sign up for Newsletter? - Update web site | 30/9 | Charu Charu Charu |
| October | - Newsletter about New year and Christmas sales is send to costumers - Update web site | 25/10 | Amish Charu |
| November | - Prepare catalogue for 2016 - Prepare trade fair 2016 - Update web site | 30/11 | Amish Amish Charu |
| December | - Catalogue for 2016 ready for print - Update web site | 15/12 | Charu Charu |

Calendar that shows what and when the activities will take place, 2015

– Example from a wholesale business in decorative art and kitchen utensils

| Activities | Jan | Feb | Mar | Apr | May | June | July | Aug. | Sep. | Oct. | Nov. | Dec. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Shop in Shop | X |  |  |  |  |  |  |  |  |  |  |  |
| Trade fair 2011 | X. | X |  |  | X |  |  |  |  |  |  |  |
| Home Party |  | X. |  |  |  |  |  |  |  |  |  |  |
| Follow up on trade fair |  | X | X |  |  |  |  |  |  |  |  |  |
| Photographer contact |  |  |  | X |  |  |  |  |  |  |  |  |
| PR articles to local news paper |  |  |  | X |  |  |  | X |  |  |  |  |
| Follow up on articles |  |  |  | x |  |  |  | X |  |  |  |  |
| Go through database |  |  |  |  | X |  |  |  | X |  |  |  |
| Plan New Year and Christmas |  |  |  |  |  | X |  |  |  | X |  |  |
| Web site update | X | X | X | X | X | X | X | X | X | X | X | X |
| Analyze Newsletter and web site |  |  |  |  |  |  |  |  | X |  |  |  |
| Send out Newsletter |  |  |  | X |  | X |  | X |  | X |  |  |
| Catalogue 2015 |  |  |  |  |  |  |  |  |  | X | X | X |

# Action plan for sales- and marketing activities, 201x

| Month | Activity we will implement: | Deadline | Responsible |
| --- | --- | --- | --- |
| January | - xxx - yyy |  |  |
| February | - - |  |  |
| March | - - |  |  |
| April | - - |  |  |
| May | - - |  |  |
| June | - - |  |  |
| July | - - |  |  |
| August | - - |  |  |
| September | - - |  |  |
| October | - - |  |  |
| November | - - |  |  |
| December | - - |  |  |

### Comments:

# Calendar that shows what and when the activities will take place, 201x

| Activities | Jan. | Feb. | Mar. | Apr. | May | June | July | Aug. | Sep. | Oct. | Nov. | Dec. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

### Comments: